## Scores
Feature | Business owner | Business value | Time criticality | Risk reduction
F1 | Passenger Experience | 13 | 8 | 8
F1 | Operations | 13 | 13 | 8
F1 | Platform | 8 | 5 | 13
F2 | Passenger Experience | 5 | 5 | 13
F2 | Operations | 13 | 20 | 13
F2 | Platform | 8 | 8 | 13
F3 | Passenger Experience | 20 | 13 | 2
F3 | Operations | 8 | 5 | 3
F3 | Platform | 3 | 2 | 1
F4 | Passenger Experience | 8 | 3 | 2
F4 | Operations | 5 | 2 | 2
F4 | Platform | 2 | 1 | 1
F5 | Passenger Experience | 13 | 5 | 3
F5 | Operations | 8 | 5 | 2
F5 | Platform | 3 | 2 | 2
F6 | Passenger Experience | 8 | 20 | 5
F6 | Operations | 5 | 8 | 3
F6 | Platform | 3 | 8 | 2
F7 | Passenger Experience | 1 | 2 | 3
F7 | Operations | 3 | 5 | 8
F7 | Platform | 8 | 13 | 20
F8 | Passenger Experience | 1 | 1 | 2
F8 | Operations | 2 | 2 | 3
F8 | Platform | 8 | 5 | 13
F9 | Passenger Experience | 13 | 8 | 5
F9 | Operations | 8 | 5 | 3
F9 | Platform | 5 | 3 | 2
F10 | Passenger Experience | 8 | 8 | 13
F10 | Operations | 13 | 13 | 13
F10 | Platform | 8 | 8 | 13

## WSJF
ID | Feature | Job size | BV average | TC average | RR average | BV median | TC median | RR median | BV spread | TC spread | RR spread | WSJF (averages) | Rank | WSJF (medians) | Rank | TC if F6 deadline is a fact | WSJF (deadline as fact) | Rank
F1 | Delay feed v2 at all major stations | 13 | 11.3333 | 8.6667 | 9.6667 | 13 | 8 | 8 | 5 | 8 | 5 | 2.2821 | 7 | 2.2308 | 3 | 8.6667 | 2.2821 | 7
F2 | Outage alerting for real-time data | 5 | 8.6667 | 11 | 13 | 8 | 8 | 13 | 8 | 15 | 0 | 6.5333 | 1 | 5.8 | 1 | 11 | 6.5333 | 1
F3 | Push notifications for all users | 8 | 10.3333 | 6.6667 | 2 | 8 | 5 | 2 | 17 | 11 | 2 | 2.375 | 6 | 1.875 | 6 | 6.6667 | 2.375 | 6
F4 | Alternative routes at night | 8 | 5 | 2 | 1.6667 | 5 | 2 | 2 | 6 | 2 | 1 | 1.0833 | 10 | 1.125 | 10 | 2 | 1.0833 | 10
F5 | Walking times for the 50 largest stations | 13 | 8 | 4 | 2.3333 | 8 | 5 | 2 | 10 | 3 | 1 | 1.1026 | 9 | 1.1538 | 9 | 4 | 1.1026 | 9
F6 | Screen-reader support across the app | 8 | 5.3333 | 12 | 3.3333 | 5 | 8 | 3 | 5 | 12 | 3 | 2.5833 | 4 | 2 | 4 | 20 | 3.5833 | 3
F7 | Logging migration for all teams | 8 | 4 | 6.6667 | 10.3333 | 3 | 5 | 8 | 7 | 11 | 17 | 2.625 | 3 | 2 | 4 | 6.6667 | 2.625 | 4
F8 | Self-service request portal | 5 | 3.6667 | 2.6667 | 6 | 2 | 2 | 3 | 7 | 4 | 11 | 2.4667 | 5 | 1.4 | 7 | 2.6667 | 2.4667 | 5
F9 | Platform-change events at all major stations | 13 | 8.6667 | 5.3333 | 3.3333 | 8 | 5 | 3 | 8 | 5 | 3 | 1.3333 | 8 | 1.2308 | 8 | 5.3333 | 1.3333 | 8
F10 | Peak-hour readiness for the delay feed | 8 | 9.6667 | 9.6667 | 13 | 8 | 8 | 13 | 5 | 5 | 0 | 4.0417 | 2 | 3.625 | 2 | 9.6667 | 4.0417 | 2
BV = business value, TC = time criticality, RR = risk reduction. Spread = highest minus lowest score of the three business owners.

## Scenarios
Capacity | Value
Velocity, last four sprints | 22 | 20 | 23 | 18
Average velocity | 20.75
Sprints in the next PI | 5
People available | 4
People today | 6
Share for bugs | 15%
Capacity for planned work (points) | 58.7917
Assumption: velocity shrinks in proportion to the people available
Item | Feature | Points | A: everything | B: top WSJF and commitments | C: rollout first
Feed v2 in Switch's test environment | F1 | 5 | 1 | 1 | 1
Feed v2 rollout: the 20 largest stations | F1 | 13 | 1 | 0 | 1
Feed v2 rollout: the other major stations | F1 | 16 | 1 | 0 | 1
Outage alerting, together with Team Depot | F2 | 13 | 1 | 1 | 1
Platform-change events at all major stations | F9 | 13 | 1 | 1 | 1
Peak-hour readiness: load test and tuning | F10 | 21 | 1 | 1 | 0
Load (points) |  |  | 81 | 52 | 60
Share of capacity |  |  | 137.8% | 88.45% | 102.1%
Fits? |  |  | no | yes | no