## Program board
Team | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | External
Signal | SIG-P3 Outage alerting for the delay feed | SIG-P2 Platform-change events at all major stations SIG-P4 Peak-hour load test and tuning | SIG-P1 Feed v2 in Switch's test environment
Switch | SWI-P1 Switch to delay feed v2 | SWI-P2 Walking times for the 50 largest stations | SWI-P3 Connection-at-risk warnings | SWI-P4 Alternative routes at night
Concourse | CON-P3 Fix duplicate push notifications | CON-P1 Push notifications for all users | CON-P2 Screen-reader support across the app | CON-P4 App release 3.3
Depot |  | DEP-P1 Logging migration for Concourse and Switch DEP-P4 Self-service request portal | DEP-P2 Monitoring rules for the delay feed DEP-P3 Peak-hour test environment DEP-P5 Release pipeline update
Outside the train | [5 empty] | Train data provider: peak-hour test data Rail Ops: text templates, connection-at-risk criteria
Red arrows on a physical board = the "late" and "missing" rows in the sheet Dependencies.

## Dependencies
# | Needs (item) | Team | Needed by sprint | From | Delivered by (item) | Delivered in sprint | Status
D1 | SWI-P1 Switch to delay feed v2 | Switch | 1 | Signal | SIG-P1 Feed v2 in Switch's test environment | 3 | late
D2 | SIG-P3 Outage alerting | Signal | 1 | Depot | DEP-P2 Monitoring rules for the delay feed | 3 | late
D3 | DEP-P2 Monitoring rules for the delay feed | Depot | 3 | Signal | Alert definitions: no item planned |  | missing
D4 | SIG-P4 Peak-hour load test | Signal | 2 | Depot | DEP-P3 Peak-hour test environment | 3 | late
D5 | SIG-P4 Peak-hour load test | Signal | 2 | Provider (outside the train) | Peak-hour test data: no date |  | missing
D6 | CON-P1 Push notifications for all users | Concourse | 2 | Signal | SIG-P2 Platform-change events at all major stations | 2 | same sprint
D7 | CON-P1 Push notifications for all users | Concourse | 2 | Rail Ops (outside the train) | Approved text templates: open |  | missing
D8 | SWI-P3 Connection-at-risk warnings | Switch | 3 | Rail Ops (outside the train) | Criteria for "at risk": open |  | missing
D9 | CON-P3 Fix duplicate push notifications | Concourse | 1 | Signal | Event feed analysis: no item planned |  | missing
D10 | SWI-P2 Walking times for the 50 largest stations | Switch | 2 | Signal | Station master data, delivered last PI | 0 | ok
D11 | CON-P4 App release 3.3 | Concourse | 4 | Depot | DEP-P5 Release pipeline update | 3 | ok
Delivered in sprint 0 = already delivered in the last PI. An empty cell = nothing planned: "missing".

## Risk register
# | Risk | Probability (1-3) | Impact (1-3) | Score | ROAM | Owner | Next step
R1 | Alerting deadlock: Signal waits for Depot's monitoring rules, Depot waits for alert definitions that nobody planned (D2, D3) | 3 | 3 | 9 | Owned | Alex and Charlie | Signal adds alert definitions to Sprint 1; joint session with Depot; Kim confirms ownership
R2 | Peak-hour load test planned before the test environment exists and without test data (D4, D5) | 3 | 3 | 9 | Mitigated | Alex | Move the load test to Sprint 4, or ask Depot for the environment in Sprint 2; test data escalation is with the steering committee
R3 | Switch cannot start on feed v2 in Sprint 1 (D1) | 3 | 2 | 6 | Mitigated | Sam | Switch starts with walking times; feed v2 work moves to Sprint 3
R4 | Push notifications need the platform-change events in the same sprint (D6) | 2 | 2 | 4 | Mitigated | Jo with Alex | Signal delivers early in Sprint 2; Concourse integrates at the end of the sprint
R5 | Rail Ops has not approved the text templates or the at-risk criteria (D7, D8) | 2 | 2 | 4 | Owned | Kim | Ask Rail Ops for both before PI Planning
R6 | Duplicate notifications may come from the event feed, but no Signal item is planned (D9) | 2 | 2 | 4 | Owned | Alex with Jo | Joint analysis in Sprint 1
R7 | Release 3.3 needs the release plan at Depot two weeks ahead (D11) | 1 | 2 | 2 | Accepted | Jo | Send the plan in Sprint 2
ROAM: Resolved, Owned, Accepted, Mitigated. Kiro proposes probability and impact; people set ROAM and owner.