## Slide 1
ART SMARTTRANSFER · PI READINESS
Ready for PI Planning, with one change of plan
Signal
Goal reached: delay feed v2 at 22 seconds in test
4 of 7 done
Switch
Goal reached: alternative routes work in test
3 of 6 done
Concourse
Goal reached: push notifications for 200 beta users
3 of 5 done
Depot
Goal not reached: logging platform for one team only
2 of 5 done
Change of plan: Team Signal has two people fewer in the next PI. The feed v2 rollout to all major stations moves to the following PI.
Sprint 14 results per team · items done of items committed

## Slide 2
PRIORITIES AND RISKS
Clear priorities, two risks that need attention
Priorities (WSJF)
1. Outage alerting for real-time data
2. Peak-hour readiness for the delay feed
Both lead in every calculation method.
Rank 3 depends on the method, and on whether the legal deadline for screen-reader support is confirmed.
Risks
Alerting deadlock between Signal and Depot: a proposal is on the table, Kim confirms who owns alert rules.
Peak-hour load test: planned before its test environment exists, and without test data.
11 dependencies: 3 late, 5 with nothing planned yet.
Source: WSJF workbook and program board of the train · calculated in Excel

## Slide 3
DECISIONS
Three decisions we need from you today
1
Escalate the late test data to the train data provider
Without data, the peak-hour test cannot run.
2
Rail Ops approves text templates once
Team Concourse writes new texts within them, checked by UX.
3
Back Depot's request form for ad-hoc requests
Incidents still go straight to on-call. Today, ad-hoc requests take around 40 % of Depot's capacity.
For your information: feed v2 in Team Switch's test environment is planned for Sprint 3. No decision needed.
AI-assisted draft · reviewed by: Agility Master, Team Signal